## Slide 1
MERIDIAN INDUSTRIAL GROUP
PROJECT ATLAS • 25 JUL 2026
Project Atlas is AMBER
Customer-context platform rollout
Status report • PRJ-ATLAS-26
AMBER
Board attention
required
Owner: Peter Molefe (EMP-009) • Sponsor: Thandi Ndlovu (EMP-003)

## Slide 2
MERIDIAN INDUSTRIAL GROUP
DELIVERY
Core build is 72% complete, but integration is two weeks at risk
72%
overall complete
14 days
schedule risk
ZAR 180k
forecast overrun
Completed
• Document ingestion API
• Invoice and proof-of-payment tokenizers
• Ontology persistence
At risk
• Approval-policy effective dating
• Contract-to-policy conflict handling
• Data-quality review workflow

## Slide 3
MERIDIAN INDUSTRIAL GROUP
DEPENDENCIES
Four linked records define the launch-critical control test
PO-2026-00418
ZAR 254,380
Manager-only approval
SI-USW-7719
ZAR 269,560
Variance ZAR 15,180
AF-2026-09
HIGH finding
Due 31 Aug
BR-2026-14
Limit changes
01 Aug 2026
Launch gate: Orgni must preserve evidence, detect the breach, and apply the board resolution prospectively—not retroactively.

## Slide 4
MERIDIAN INDUSTRIAL GROUP
NEXT DECISION
Hold launch until trustworthy-context gates pass
1
Entity resolution
Resolve Ubuntu’s three aliases without merging Eastern Bearings.
2
Policy reasoning
Detect PO authority breach and agreement-policy conflict.
3
Temporal truth
Keep FL-07 correction and 01 Aug authority change effective-dated.
4
Transaction linkage
Link order, delivery, invoice and partial payment with provenance.
Decision owner: Naledi Mokoena • Evidence pack: MIG-ORGNI-HARDTEST-2026-01